## Gantt Chart
# | Task | Owner | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30
|  |  | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI
1 | Study and understand the requirements | Husny | MON: 8
2 | Requirement clarification with the product owner | Both | TUE: 8
3 | Test Planning & Define in-scope and out-of-scope for testing | Both | WED: 4
4 | Create test cases for UI & API level testing | Husny | THU: 8; FRI: 8; MON: 8; TUE: 8; WED: 8
5 | Review test cases and test data | Apurwa | THU: 4
6 | Modify test cases based on review comments | Husny | FRI: 4
7 | Hand over critical test cases to the dev team and wait till dev testing is completed. | Dev | bar: MON to WED
8 | Execute test cases & Defect Reporting | Husny | THU: 8; FRI: 8; MON: 8; TUE: 8; WED: 8; THU: 8
9 | Defect retesting | Husny | FRI: 8; MON: 8; TUE: 8
10 | Regression testing to cover impacted areas | Husny | WED: 8
11 | Feature demo | Husny | THU: 2
12 | Provide Sign-Off | Husny
13 | Production sanity check | Husny | FRI: 4
14 | Documentation | Husny | MON: 4
15 | Define labels, tags, and prefixes to manage test cases and defects | Husny | bar: TUE
16 | Create a dashboard in Jira | Husny | WED: 2
17 | Test data creation for dev testing | Husny | THU: 4; FRI: 4
18 | API Automation |  | TUE: 8; WED: 8
19 | Retrospective with the team | Husny | THU: 2
20 | Knowledge sharing with the team | Husny | FRI: 4
|  |  | 8 | 8 | 6 | 8 | 8 | 8 | 9 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development and dev testing must be completed
QA Sign-Off
Husny is on leave